## Sheet1
MONTAUKETT LEARNING RESOURCE CENTER (CP 2189)
CHANGE ORDER SUMMARY
2010-10-28
Attachment III
Original Construction Budget |  | 11620000
Original Construction Contracts to Date | 11199561
Approved Change Orders Billed to Project to Date | 30125
Reimbursable Expenses | 9502.61
Materials Testing | 51183.4
EW Howell Major Change Order No. 3 | 118378
Pending Change Orders (Approximate) | 50000
Estimated Cost of Project Construction to Date | 11458750.01 | 11458750.01
Estimated Project Construction Balance Available |  | 161249.99