## Sheet1
SUFFOLK COMMUNITY COLLEGE
NEW LIFE SCIENCES BUILDING
J. PETROCELLI CHANGE ORDERS
FEBRUARY 2014
College | Item | Description | Cost | Approval |  | Fund
Change Order |  |  |  | Date | Method
1 | 1 | Exploratory work to uncover discovered sewer structures | 2130.59 | Mar. 6, 2013 | College Administration | Science Bldg. (2174)
| 2 | Exploratory work to uncover and map discovered sewer lines and leaching pools | 5911.44 | Mar. 6, 2013 | College Administration | Science Bldg. (2174)
| 3 | Exploratory work to uncover additional sewer lines, leaching pools and concrete debris | 5529.47 | Mar. 6, 2013 | College Administration | Science Bldg. (2174)
| 4 | Abandon and/or incorporate discovered sewer lines and leaching pools | 103538.91 | Feb. 21, 2013 | BOT Reso. 2013.17 | Science Bldg. (2174)
2 | 1 | New President's Cottage sewer connection and abandonment of old sewer system | 76309.19 | Mar. 21, 2013 | BOT Reso. 2013.21 | Infrastructure (2149)
3 | 1 | Excavation and removal of 10 additional underground drainage structures | 32319.02 | Apr. 18, 2013 | BOT Reso. 2013.31 | Science Bldg. (2174)
4 | 1 | Add Alternate No. 38 - 5 inch mullions on curtain wall | 58000 | June 20, 2013 | BOT Reso. 2013.44 | Science Bldg. (2174)
| 2 | Incorporate existing road drainage into project site drainage | 27603.38 | Sept. 19, 2013 | BOT Reso. 2013.63 | Science Bldg. (2174)
| 3 | Credit for work not performed on the new President's Cottage sewer system | -22521 | Sept. 19, 2013 | BOT Reso. 2013.63 | Infrastructure (2149)
| 4 | Additional buried debris found during excavation | 1716.84 | Sept. 19, 2013 | BOT Reso. 2013.63 | Science Bldg. (2174)
| 5 | Underground conduit for future photovoltaic system | 6600.79 | Sept. 19, 2013 | BOT Reso. 2013.63 | Science Bldg. (2174)
| 6 | Additional clearing required for fence line | 1228.25 | Sept. 19, 2013 | BOT Reso. 2013.63 | Infrastructure (2149)
5 | 1 | Additional asphalt overlay in Annex parking lot | 10450 | Sept. 19, 2013 | BOT Reso. 2013.63 | Infrastructure (2149)
| 2 | Additional stripping for 'no parking' areas in Annex parking lot | 5170 | Sept. 19, 2013 | BOT Reso. 2013.63 | Infrastructure (2149)
| 3 | Concrete inspection cancellation | -125 | Sept. 19, 2013 | BOT Reso. 2013.63 | Science Bldg. (2174)
| 4 | Loading stockpiled soil for reclamation | 3763.87 | Sept. 19, 2013 | BOT Reso. 2013.63 | Science Bldg. (2174)
6 | 1 | Removal of abandoned concrete drainage swale | 5469.78 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
| 2 | Install four wheel stops in Parking Lot #1 | 648.3 | Dec. 5, 2013 | BOT Reso. 2013.85 | Infrastructure (2149)
| 3 | Add conduit to observatory for telecommunication to telescope | 3202.38 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
| 4 | Extend telecommunications run from Riverhead Bldg. basment to IT closet | 12295.79 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
| 5 | Substitute RCA subgrade for bluestone under first floor slab | -10188.81 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
| 6 | Add Alternate #25 - Video Wall | 68800 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
| 7 | Add Alternate #48 - Dashborad | 35600 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
7 | 1 | Electronic card reader software and hardware installation for doors | 141989.91 | Feb. 20, 2014 | Pending | Science Bldg. (2174)
Minor Change Orders |  |  | 58886.07
Major Change Orders |  |  | 516557.03
Total Change Orders |  |  | 575443.1
New Life Science Building Budget Remaining (2174) |  |  | 935000