## Sheet1
SUFFOLK COMMUNITY COLLEGE
NEW LIFE SCIENCES BUILDING
J. PETROCELLI CHANGE ORDERS
JUNE 2014
College | Item | Description | Cost | Approval |  | Fund
Change Order |  |  |  | Date | Method
1 | 1 | Exploratory work to uncover discovered sewer structures | 2130.59 | Mar. 6, 2013 | College Administration | Science Bldg. (2174)
| 2 | Exploratory work to uncover and map discovered sewer lines and leaching pools | 5911.44 | Mar. 6, 2013 | College Administration | Science Bldg. (2174)
| 3 | Exploratory work to uncover additional sewer lines, leaching pools and concrete debris | 5529.47 | Mar. 6, 2013 | College Administration | Science Bldg. (2174)
| 4 | Abandon and/or incorporate discovered sewer lines and leaching pools | 103538.91 | Feb. 21, 2013 | BOT Reso. 2013.17 | Science Bldg. (2174)
2 | 1 | New President's Cottage sewer connection and abandonment of old sewer system | 76309.19 | Mar. 21, 2013 | BOT Reso. 2013.21 | Infrastructure (2149)
3 | 1 | Excavation and removal of 10 additional underground drainage structures | 32319.02 | Apr. 18, 2013 | BOT Reso. 2013.31 | Science Bldg. (2174)
4 | 1 | Add Alternate #38 - 5 inch mullions on curtain wall | 58000 | June 20, 2013 | BOT Reso. 2013.44 | Science Bldg. (2174)
| 2 | Incorporate existing road drainage into project site drainage | 27603.38 | Sept. 19, 2013 | BOT Reso. 2013.63 | Science Bldg. (2174)
| 3 | Credit for work not performed on the new President's Cottage sewer system | -22521 | Sept. 19, 2013 | BOT Reso. 2013.63 | Infrastructure (2149)
| 4 | Additional buried debris found during excavation | 1716.84 | Sept. 19, 2013 | BOT Reso. 2013.63 | Science Bldg. (2174)
| 5 | Underground conduit for future photovoltaic system | 6600.79 | Sept. 19, 2013 | BOT Reso. 2013.63 | Science Bldg. (2174)
| 6 | Additional clearing required for fence line | 1228.25 | Sept. 19, 2013 | BOT Reso. 2013.63 | Infrastructure (2149)
5 | 1 | Additional asphalt overlay in Annex parking lot | 10450 | Sept. 19, 2013 | BOT Reso. 2013.63 | Infrastructure (2149)
| 2 | Additional stripping for 'no parking' areas in Annex parking lot | 5170 | Sept. 19, 2013 | BOT Reso. 2013.63 | Infrastructure (2149)
| 3 | Concrete inspection cancellation | -125 | Sept. 19, 2013 | BOT Reso. 2013.63 | Science Bldg. (2174)
| 4 | Loading stockpiled soil for reclamation | 3763.87 | Sept. 19, 2013 | BOT Reso. 2013.63 | Science Bldg. (2174)
6 | 1 | Removal of abandoned concrete drainage swale | 5469.78 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
| 2 | Install four wheel stops in Parking Lot #1 | 648.3 | Dec. 5, 2013 | BOT Reso. 2013.85 | Infrastructure (2149)
| 3 | Add conduit to observatory for telecommunication to telescope | 3202.38 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
| 4 | Extend telecommunications run from Riverhead Bldg. basment to IT closet | 12295.79 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
| 5 | Substitute RCA subgrade for bluestone under first floor slab | -10188.81 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
| 6 | Add Alternate #25 - Video Wall | 68800 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
| 7 | Add Alternate #48 - Dashborad | 35600 | Dec. 5, 2013 | BOT Reso. 2013.85 | Science Bldg. (2174)
7 | 1 | Electronic card reader software and hardware installation for doors | 141989.91 | Feb. 20, 2014 | BOT Reso. 2014.19 | Science Bldg. (2174)
| 2 | Rebar inspection cancelation | -325 | Apr. 21, 2014 | College Administration | Science Bldg. (2174)
| 3 | Instructional podium replacement | 148.83 | Apr. 21, 2014 | College Administration | Science Bldg. (2174)
8 | 1 | Additional HVAC hot water valves to isolate individual floors | 5278.67 | Pending | BOT Reso. 2014.59 | Science Bldg. (2174)
| 2 | Relocate Siamese connection for fire protection piping as per Fire Marshal | 11535.7 | Pending | BOT Reso. 2014.59 | Science Bldg. (2174)
| 3 | Additional sprinkler system drain valves to isolate individual floors | 10382.9 | Pending | BOT Reso. 2014.59 | Science Bldg. (2174)
| 4 | Additional three sprinkler heads in stair wells | 5164.5 | Pending | BOT Reso. 2014.59 | Science Bldg. (2174)
| 5 | Furnish 18 access panels for laboratory casework maintenance access | 4840 | Pending | BOT Reso. 2014.59 | Science Bldg. (2174)
| 6 | Modify east stormwater system; extend fire access road as per Fire Marshal | 28916.05 | Pending | BOT Reso. 2014.59 | Science Bldg. (2174)
Minor Change Orders |  |  | 95911.67
Major Change Orders |  |  | 545473.08
Total Change Orders |  |  | 641384.75
New Life Science Building Construction Budget Remaining |  |  | 850756

## Sheet2
Budget | 1090640.77
Pending
Swipe cards | 141989.91
Rebar cancel | -325
Nova | 0
Sprinkler isolation valves
HVAC isolation valves
Furniture
Fire marshal connection
Fire road
Testing | 19804
AV | 68500
IT | 363000
Total | 592968.91
Remaining | 497671.86
PV

## Sheet2 (2)
Budget | 1082121.77 | ($1,090,640 in construction; $26,124 in FF&E)
26124
| 1108245.77 |  |  |  | Testing
Pending |  |  |  |  | feb
mar
Swipe cards | 141989.91 |  |  |  | Apr
Rebar cancel | -325 |  |  |  | may
Nova | 148.83 |  |  |  | June
Sprinkler isolation valves | 10269.6 |  |  |  | july
HVAC isolation valves | 6376.74 |  |  |  | aug
Furniture
Fire marshal connection | 11727.89 |  | 1090640.77
Naming Letters |  |  | 1082121.77 | 1082121.77
Fire road |  |  | 8519 | 26124
Testing | 10625 |  |  | 1108245.77
AV | 68500
IT | 363000
Total | 612312.97
Remaining | 495932.8
Pending Testing | 50000
Left | 445932.8
Needs
PV | 700000
Rosa | 960000
1660000
New Request | 1214067.2